## TIMELINE
Due Date | Project Phase | Summary Description | Assigned To
6-8 months out | Event Approval | Co-Chairs have met with ADRP Office and received approval to plan event | Co-Chairs
6-8 months out | Venue/Date | Venue and Date confirmed with ADRP Office | Co-Chairs
6-8 months out | Committee | Conference committee kick-off meeting - Identify Subcommittee Leads | Co-Chairs
6-8 months out | Committee | Develop committee meeting calendar | Co-Chairs
6-8 months out | Marketing/Communication | Develop communications content calendar | Communications Lead
6-8 months out | Sponsors/Exhibitors | Determine sponsorship & exhibit booth rates | Sponsorship Lead
6-8 months out | Finance | Draft Budget sent to Office | Co-Chairs
6-8 months out | Sponsors/Exhibitors | Create sponsorship prospectus | Sponsorship Lead
6 months out | Venue | Deposit to venue | Logistics Lead
6 months out | Website | Create Landing page and update the regional event calendar | ADRP Office
6 months out | Sponsors/Exhibitors | Launch sponsor & vendor solicitations | Sponsorship Lead
6 months out | Marketing/Communication | Save the Date Eblast to Region | Communications Lead
6 months out | Finance | Budget finalized and approved by ADRP Office | Co-Chairs
5 months out | Presenter/Speaker | Launch RFP | Content Lead
5 months out | F&B | Begin working on F&B needs | Logistics Lead
5 months out | Marketing/Communication | Speaker RFP reminder email | Content Lead
4 months out | Marketing/Communication | Speaker RFP reminder email | Content Lead
4 months out | Presenter/Speaker | Close Speaker RFP | Content Lead
3 months out | Hotel | Identify Hotels for room block(s) | Attendee Experience Lead
3 months out | Presenter/Speaker | Committee to finalize speaker selections | Content Lead
3 months out | Logistics | Update ADRP PowerPoint Presentation Template for speakers | Communications Lead
3 months out | Presenter/Speaker | Send speaker selection notification emails | Content Lead
3 months out | Presenter/Speaker | Deadline: Presentation description and bios due | Content Lead
3 months out | Presenter/Speaker | Breakout schedule & session assignments finalized | Content Lead
3 months out | Website | Post session information online | Communications Lead
3 months out | Registration | Open registration | ADRP Office
3 months out | Marketing/Communication | Marketing email: speaker announcements and reg open | Communications Lead
2 months out | Marketing/Communication | Registration reminder email | Communications Lead
2 months out | Venue | Certificate of Insurance Due | Logistics Lead
4 weeks out | Certification | CFRE Credits | ADRP Office
4 weeks out | Sponsors/Exhibitors | Reach out to Sponsors/Exhibitors re: missing info | Sponsorship Lead
4 weeks out | Logistics | Determine happy hour and pre-conference dinner info | Attendee Experience Lead
4 weeks out | Marketing/Communication | Registration reminder email | Communications Lead
4 weeks out | Logistics | Make speaker room assignments | Logistics Lead
4 weeks out | Venue | Final payment due to venue | Logistics Lead
4 weeks out | Sponsors/Exhibitors | Deadline: Sponsor logos and ads due to office | Sponsorship Lead
4 weeks out | Design & Printed Materials | Office to send logos and sponsor ads for program | Communications Lead
4 weeks out | Presenter/Speaker | Deadline: Speaker presentations/handouts due | Content Lead
3 weeks out | Design & Printed Materials | Design program & welcome PowerPoint slides | Communications Lead
3 weeks out | Design & Printed Materials | Final program due to Office for printing | Communications Lead
3 weeks out | Presenter/Speaker | Confirm that all speakers have registered with discount code | Content Lead
3 weeks out | Logistics | Determine registration set-up | Logistics Lead
3 weeks out | Logistics | Determine room sets | Logistics Lead
3 weeks out | Logistics | Determine venue flow | Logistics Lead
3 weeks out | Audio Visual (AV) | Determine AV needs | Logistics Lead
2 weeks out | Volunteers | Recruit onsite volunteers | Attendee Experience Lead
2 weeks out | Marketing/Communication | Final Registration reminder email | Communications Lead
2 weeks out | Registration | Close Registration | ADRP Office
2 weeks out | Marketing/Communication | Attendee Communication: Know Before You Go | Attendee Experience Lead
2 weeks out | Sponsors/Exhibitors | Sponsor/Exhibitor Communication: Know Before You Go | Sponsorship Lead
2 weeks out | F&B | Review BEOs - Mark up changes & finalize | Logistics Lead
2 weeks out | Audio Visual (AV) | Finalize AV needs | Logistics Lead
2 weeks out | Design & Printed Materials | Print name badges & program and ship to venue | ADRP Office
1 week out | Logistics | Make reservations for pre-conference dinner | Attendee Experience Lead
1 week out | F&B | Guarantees & signed BEOs due to venue | Logistics Lead
1 week out | Design & Printed Materials | Print registration, sponsor and session room signage | Communications Lead
1 week out | Sponsors/Exhibitors | Email booth assignments to exhibitors | Sponsorship Lead
Event Day! |  | Event Date | -
1 week post | Marketing/Communication | Attendee Communication: Evaluation/Thank You | Communications Lead
1 week post | Presenter/Speaker | Sponsor/Exhibitor Communication: Evaluation/Thank You | Sponsorship Lead
1 week post | Venue | Settle final venue bill | Logistics Lead
2 weeks post | Evaluation | Distribute evaluation results to committee | Co-Chairs